## Slide 1
Field | Details
Business Case Title | HR Process Optimization at Synergy Enterprises
Submitted To | Global Board of Directors
Submitted By | Uduak Doris Frank / Business Analyst
To the Attention of | Global Board Members
Point of Contact | Uduak Doris Frank
Address | 1 Unity Avenue Road, Grace Villa.
Phone (Local) | +234 800 000 000
Phone (International) | +1 900 0000
Email | udorisfrank@gmail.com
Date Submitted | 23rd September, 2025
Delivery Method | Physical submission

## Slide 2: Executive Summary
Synergy Enterprises current fragmented HR Technology Landscape is a significant operational and strategic liability. With each region running disparate HR systems from legacy payroll tools to spreadsheets for performance management , we lack a single, unified view of our global workforce. This “fragmented system "creates duplicated data, slows down HR processes, and prevents us from generating the global insights needed to plan talent, ensure adherence, and build a consistent employee experience.
The result is inefficient operations, Heightened regulatory exposure, higher IT costs, and a disjointed employee journey that undermines our ability to project a Cohesive Global Brand.
We recommend the deployment of a centralized, cloud-based Human Resource Information System (HRIS) to unify all HR functions, Recruitment, Onboarding, Payroll, Performance management, and Regulatory adherence into one global Platform.
This solution will streamline operations, reduce errors ensure regulatory conformity across jurisdictions, and deliver a consistent experience to our 75,000+ employees worldwide.
This Project is directly aligned with our corporate objective to build a consistent and strong global brand image. The new HRIS will deliver measurable results:
25% increase in operational efficiency,
$5 million in annual savings within three years, and
15% boost in employee satisfaction through a standardized, seamless experience.

## Slide 3: Financial Analysis (Cost–Benefit Review)
Option | Estimated Costs | Key Benefits | Net Value
1. Status Quo (Do Nothing) | Minimal (ongoing IT support $8–10M annually) | No disruption in short term. | Negative: Costs persist; inefficiencies, fines, and attrition outweigh savings.
2. Partial Integration | $25–30M (integration tools, consulting, training) | Faster fixes for data flow, modest efficiency gains, lower short-term disruption. | Moderate Positive: 10–12% efficiency gain, $15M savings, but fragile long-term.
3. Global Cloud-Based HRIS | $75–100M over 3 years (licensing, migration, training, change management) | Unified workforce data, 25% efficiency gain, $5M annual savings after 3 years, 15% higher employee satisfaction. | High Positive (Long-Term): Major efficiency and savings, but requires large upfront capital.

## Slide 4: Proposed Solution / Review of Options
To address the operational and strategic failures caused by Synergy Enterprises’ fragmented HR systems, we have evaluated three distinct approaches:
Option | Description | Impact
1. Status Quo (Do Nothing) | Maintain existing fragmented regional HR systems. | Persistent inefficiencies, rising IT costs, regulatory exposure, and further damage to brand.
2. Partial Integration | Connect current HR tools via middleware and custom interfaces. | Short-term relief; high complexity, fragile integrations, limited scalability, and high costs.
3. Global Cloud-Based HRIS (Preferred) | Deploy a unified Human Capital Management platform covering Recruitment, Onboarding, Payroll, Performance, and Regulatory Adherence. | One global workforce view, Automation, Consistent employee experience, Reduced costs, and Improved compliance.

## Slide 5: Recommendations
To address Synergy Enterprises most urgent HR challenges while maintaining financial discipline, and in line with KPMG’s feasibility study projecting recovery within five years, we recommend a phased approach.
Year 0–5 (Interim Phase):
Implement Aggregation of Existing Applications
Minimal upfront cost, rapid deployment
Immediate relief for HR inefficiencies
Supports compliance and operational stability during financial recovery
Year 5+ (Long-Term Phase):
Transition to Full-Scale Global Cloud HRIS
Unified workforce view, automation, advanced analytics
Significant efficiency gains, cost savings, and stronger global employer brand
.

## Slide 6: Implementation Plan – Aggregation of Disparate Applications
The implementation will follow a four-phase plan spanning (9) nine months, outlined below.
Phase | Timeline | What Happens | Outcome
1. Assessment & Planning | Months 1–2 | Review all existing HR tools, identify overlaps, and decide which systems to connect. | Clear map of systems and integration priorities.
2. Design & Configuration | Months 3–4 | Set up how the systems will “talk” to each other, organize employee data, and create common formats. | A working design that connects systems smoothly.
3. Pilot & Testing | Months 5–6 | Try the new setup in one region or department, check for errors, and gather staff feedback. | Issues fixed early, proof that the system works.
4. Full Rollout & Stabilization | Months 7–9 | Apply the setup across all regions, train HR teams, and monitor performance. | Company-wide system in place and working reliably.

## Slide 7: Implementation Risk and Mitigation
Implementation Risk and Mitigation Some risk has been identified for the implementation of the project. They are highlighted;
Risk | What Could Happen | Mitigation (How We Handle It)
Change Resistance | Employees may resist switching from familiar tools to the new integrated setup. | Early communication, training sessions, and visible leadership support.
Data Migration Errors | Some employee data may be lost, duplicated, or mismatched during integration. | Careful data cleaning, pilot testing, and validation before rollout.
System Downtime | Integration work could cause disruptions in HR services during transition. | Phased rollout with fallback options to ensure continuity.
Cost Overruns | Expenses may exceed budget due to unexpected complexity. | Strict project governance, regular budget reviews, vendor accountability.
Security & Compliance Risks | Mishandling of sensitive workforce data could result in privacy breaches, regulatory fines, and reputational damage. | Conduct a security and compliance audit at each project phase; enforce data access controls, encryption standards, and adherence to regulations such as GDPR and local labor laws.

## Slide 8: Conclusion
Given the serious operational risks and financial pressures, we request immediate approval to proceed with the Aggregation of Existing Applications. This phased, fiscally disciplined strategy offers a timely solution to today’s HR challenges while safeguarding Synergy Enterprises’ financial stability.
Approval will authorize the project team to begin with Phase 1: Assessment & Planning, with overall completion expected within (9)nine months. This initiative will deliver meaningful efficiency gains.

## Slide 9: Thank you